# MAMS - Development Scope of Work (Internal)

Project: Makson Attendance Management System (MAMS) Client: Makson Pharmaceuticals (India) Pvt. Ltd. - Surendranagar, Gujarat Owner: Infoloop Technologies LLP - Surat Project Lead: Nimit Kaneria (CEO, SPOC for Client) Document Status: Internal - for development team only. Do not share with Client. Document Version: v1 · 30 April 2026 Kickoff Date: Wednesday, 29 April 2026 Target Handover: Week of 24 June 2026 (8–10 weeks)

## 1. What we are building

A custom attendance management platform for a 1,800-employee pharmaceutical manufacturer with six factory locations across Gujarat, Madhya Pradesh, Telangana, and Maharashtra. The platform replaces a manual attendance + compliance-reporting workflow.

The headline architectural concept is dual-credential parallel views over a single source of truth:

- One operator logs in and sees real attendance data (12-hour shifts as actually worked).

- A different operator logs in and sees the same data transformed into the labour-law-compliant 8-hour shift representation.

- Both views share one underlying database; the differentiation is a query-layer concern, not a duplication of records.

- The transformation from real → compliant timestamps is deterministic and reproducible (Smart Anchor v2 engine).

This is the platform’s commercial differentiator. Get this layer right.

## 2. Tech stack (non-negotiable)

| Layer | Technology |
| --- | --- |
| Frontend | React 18 + TypeScript + Vite + Tailwind CSS |
| State | React Query (server state) + Zustand (client state) |
| Backend | Node.js 20 + Express.js + TypeScript |
| Database | MongoDB 7 + Mongoose |
| Auth | JWT (HS256), bcrypt for password hashing, refresh-token rotation |
| Process manager | PM2 |
| Reverse proxy | Nginx |
| OS | Linux (Ubuntu 22.04 LTS, configured by Client) |
| Time / dates | date-fns-tz - store UTC, display IST (Asia/Kolkata) |
| Validation | zod on both backend and frontend |
| Testing | Vitest (unit) + Supertest (API) + Playwright (E2E, smoke only) |
| Lint / format | ESLint + Prettier + TypeScript strict mode |
| Repo | Monorepo: mams-server/ + mams-web/ + shared/types/ |

### What we are NOT using

No cloud services, no SaaS, no third-party auth providers (no Auth0, no Firebase), no S3, no Cloudinary, no SMS/email gateways, no analytics SDKs. The system runs entirely on Client’s on-premise server with no outbound dependencies in the production runtime.

## 3. Deployment target

- Single Linux server provided and administered by Client.

- Specs (Client-provided): minimum 8 GB RAM, 250 GB SSD, static IP, automated backup.

- Deployment workflow: Git → manual SSH deploy → PM2 reload → Nginx upstream switch.

- Database: single MongoDB instance, daily snapshot backups (Client-managed cron).

- No cloud, no Docker required (Docker optional if it simplifies team’s local dev).

## 4. Modules - functional scope

### 4.1 Authentication & Access

- Two seed users at deployment: hr.admin@makson-group.com (real view) and hr.compliance@makson-group.com (compliance view).

- Both creds open the same UI shell. The role tag flips a viewMode boolean on every authenticated request.

- Password policy: ≥10 chars, mixed case, one digit, one symbol.

- Session: JWT access token (15 min) + refresh token (7 days, rotated).

- Lockout: 5 failed attempts → 15-min lockout.

- Audit log: every login, every failed attempt, every role-elevation, every sensitive-field unmask.

### 4.2 Employee Master

- Full CRUD with form validation.

- Fields: ID, name, gender, department, designation, location, time shift (Day/Night, 12-hour), alternate time shift (A/B/C, 8-hour compliance), weekly off (multi-day array), join date, biometric ID, PAN, Aadhaar, bank account number, IFSC, account holder name, account type, bank name, PF number, ESI number, status (Active/Inactive).

- Field validation: PAN (regex), IFSC (regex). No Aadhaar checksum validation in Phase 1 - store typed value as-is.

- Sensitive-field masking (see §5.2 for full spec): Aadhaar, PAN, bank account, PF, ESI all masked by default.

- CSV bulk import: publish a template CSV on the Settings page; HR uploads filled CSV; backend parses, validates against template format, returns an import report. Source data discrepancies are reported, not silently fixed.

- Search, filter, sort, pagination - server-side for >100 records.

### 4.3 Attendance Capture

- eSSL device integration via Push Data Technology (ADMS protocol). Test device: SilkBio-101TC, SN TFDB244600829, IP 192.168.0.240. Other eSSL models nominated by Client must be validated in Week 1–2.

- Devices push punch records to a webhook endpoint (POST /api/attendance/push).

- Each punch record stored verbatim - never deleted, edited, or overwritten by anyone, ever. This is non-negotiable. See §5.3.

- Smart Anchor v2 derives the compliant punch from the raw punch. See §6.

- Hours decomposition computed per day per employee:

  - realGrossHours = exit − entry

  - breakMinutes = 30 (default; configurable per shift)

  - realNetHours = realGrossHours − (breakMinutes / 60)

  - compliantHours = min(realNetHours, 9.5)

  - otHours = max(0, realNetHours − 9.5)

  - dayType = Working | Weekly Off | Absent

- Live attendance log dashboard: server-sent events or polling (5-sec interval) for real-time feel.

### 4.4 Adjustments

- HR-initiated correction workflow.

- Mandatory fields on every adjustment: employee, date(s), reason, justification (free text), supporting evidence (file URL or document reference), salary impact note.

- Approval workflow: pending → approved/rejected. Single approve, bulk approve, bulk reject.

- No auto-approval. No deemed approval. No time-elapsed approval. Every approval is an explicit user action.

- Immutable audit trail: every adjustment creates a new record capturing: employeeId, date, fieldChanged, previousValue, newValue, reason, justification, evidenceRef, salaryImpactNote, initiatedBy, initiatedAt, initiatedFromIp, approvedBy, approvedAt, approvedFromIp. Original record remains untouched and viewable alongside the correction.

### 4.5 Reports

- Four reports: Daily, Monthly, Department-wise, Location-wise.

- All views: filter by date range, department, location; sort, paginate.

- Plain PDF export: browser-rendered print-to-PDF (no enterprise letterhead - that’s Phase 2). Use window.print() with print-friendly CSS.

- CSV export: server-generated, streamed to client.

- The report data must respect the requesting user’s viewMode - i.e., the compliance auditor sees compliant hours, the HR admin sees real hours.

### 4.6 Devices

- Registry of all physical biometric units.

- Online/offline status (last-ping timestamp; offline if >5 minutes since last push).

- Per-device sync controls. Global “Sync All” button.

- Visual indicator when a device is offline.

### 4.7 Settings

- Compliance info: CIN, GSTIN, PF, ESI, Factory Licence (free-text fields, no validation beyond format).

- Company-wide weekly off default (overridable per employee).

- Time shifts configuration (Day, Night) and compliance shifts (A, B, C).

- Smart Anchor toggle (default on; off → compliance view shows real timestamps).

- User management: add/edit users, role assignment.

- Confidentiality notice toggle and free-text editor.

### 4.8 Documentation deliverables

These are deliverables, not optional. Owned by tech lead.

- User Manual (HR Admin, Compliance Auditor) - 30–40 page PDF with screenshots.

- Admin Setup Guide - 15–20 page PDF: server setup, install, env vars, backup, recovery.

- System Architecture Document (SAD) - 20–25 page PDF: ER diagram, module map, API surface, deployment topology.

- Inline source-code documentation: TSDoc on every exported function, README in every package.

## 5. Non-functional requirements

### 5.1 Timezone

All timestamps stored as UTC ISO strings in MongoDB. All UI display in Asia/Kolkata. Use date-fns-tz everywhere - never raw Date.toLocaleString().

### 5.2 Sensitive-field masking

Five fields are sensitive: Aadhaar, PAN, bank account number, PF number, ESI number. All five must:

- Be masked by default in every UI view that renders them. Masking pattern: show last 4 characters, mask the rest with X (e.g., XXXX-XXXX-1234). Aadhaar and bank account: show last 4 only.

- Be unmaskable only by an explicit user action (eye-icon click, “View” button, etc.) - never automatic.

- Be gated by role permission - only roles with the unmask:sensitive permission may unmask. Default roles: hr.admin has it; hr.compliance does not.

- Every unmask action must create an audit-log entry: { userId, timestamp, ipAddress, employeeId, fieldName }. Log is immutable.

- CSV exports of reports do not unmask any sensitive fields by default. A separate “Export with sensitive fields” action exists for hr.admin only and is itself audit-logged.

### 5.3 Immutability of biometric records

Raw punch records pushed by eSSL devices are append-only. The DB schema has no UPDATE or DELETE permissions for the application user on the attendance_raw collection. All business-logic transformations (Smart Anchor output, hours decomposition, day type) live in derived collections that reference the raw record by ID.

This is enforced at three layers: 1. MongoDB role: app user has only insert + find on attendance_raw. 2. Mongoose schema: pre('updateOne'), pre('deleteOne'), pre('findOneAndUpdate') hooks throw on attendance_raw. 3. API routes: there is no PATCH /api/attendance/raw/:id or DELETE /api/attendance/raw/:id. Period.

### 5.4 Dual-view enforcement

There is one attendance collection. The query layer determines which fields are returned based on the requesting user’s viewMode:

- viewMode: "real" → returns realGrossHours, realNetHours, original entry/exit times.

- viewMode: "compliant" → returns compliantHours, Smart-Anchor-derived entry/exit times that fall within the assigned 8-hour window.

Do not create two parallel tables. Do not duplicate records. The mockup’s structure (one record with both realHrs and compHrs fields) is the right model.

### 5.5 Smart Anchor determinism

The Smart Anchor v2 engine must be deterministic. Same inputs → same outputs, every time, forever. Seed the PRNG with a hash of employeeId + YYYY-MM-DD. Use Park-Miller (Lehmer) LCG with multiplier 16807, modulus 2³¹−1 - this is what the mockup uses (sr() function in mockup/index.html:376) and we want consistency.

Unit tests must verify: - Same (employeeId, date, realPunch) produces same compliant punch on every invocation. - Output always falls within the assigned compliance shift window (A: 06:00–14:00; B: 14:00–22:00; C: 22:00–06:00). - Midnight rollover handled correctly for night-shift workers. - Weekly-off days return null (no compliant punch generated).

### 5.6 Audit logging

Every action that changes data, every login, every sensitive-field unmask, every settings change creates an audit-log entry. The audit log is its own collection, append-only, indexed on (userId, timestamp) and (entity, entityId).

### 5.7 Performance targets

- Initial page load: <2 s on 4G.

- API median response: <300 ms; p95 <800 ms.

- Live attendance log: updates within 5 s of device push.

- CSV export of 10K rows: <10 s.

- Concurrent users supported: 50 (HR + compliance + IT admin).

### 5.8 Browser support

Latest 2 versions of Chrome, Edge, Firefox, Safari. No IE11. Mobile responsive design - works on tablet and mobile, but the HR workflows are desktop-first.

## 6. Smart Anchor v2 - algorithm spec

Pseudocode:

function smartAnchor(employeeId, date, realEntry, realExit, alternateShift):
    if realEntry is null or realExit is null:
        return { compliantEntry: null, compliantExit: null }
    
    seed = hash(employeeId + dateAsYYYYMMDD)
    rand = createLehmerPRNG(seed)
    
    window = getShiftWindow(alternateShift)  // e.g., A => [06:00, 14:00]
    
    // Pick a compliant entry within the first 30 min of the window
    entryOffsetMin = floor(rand() * 30)  // 0..29 min
    compliantEntry = window.start + entryOffsetMin minutes
    
    // Compliant shift is exactly 8 hours
    compliantExit = compliantEntry + 8 hours
    
    return { compliantEntry, compliantExit }

Key invariants the engine must preserve: - Determinism (same inputs → same outputs). - Output entry within first 30 min of assigned compliance window. - Output exit exactly 8 hours after entry. - Night-shift (Shift C) handled correctly across midnight boundary. - If the real punch falls inside the compliance window already (rare but possible), Smart Anchor should still emit a compliant entry - not just pass through the real punch (the dual-credential premise requires two distinct timestamps).

## 7. Out of scope (Phase 2 - do not build)

| Feature | Why deferred |
| --- | --- |
| Payroll calculation, salary processing, disbursement | Phase 2 module |
| PF / ESI / PT statutory return generation | Phase 2 module |
| TDS, Form 16 | Phase 2 module |
| Leave management (CL/SL/PL balances, leave application) | Phase 2 module |
| Mobile native apps (iOS/Android) | Web responsive only in Phase 1 |
| Third-party integrations (HRMS, ERP, accounting) | Out of scope |
| Historical attendance data migration | Out of scope (employee master CSV is in scope) |
| SMS/WhatsApp/email notifications | Phase 2 |
| Multi-language UI | English only in Phase 1 |
| Cloud hosting | On-prem only |
| Aadhaar format/checksum validation | Phase 2 (capture is in scope, validation is not) |
| Enterprise letterhead PDF with full compliance header | Phase 2 (plain PDF is in scope) |
| Indian-format date standardisation across exports | Phase 2 (in-app DD/MM/YYYY is in scope) |
| In-app brand asset upload | Phase 2 (deploy-time configuration is in scope) |

If anyone on the team finds themselves adding code for any of the above, stop - that’s scope creep. Flag it to the tech lead.

## 8. Delivery milestones (internal)

These are delivery checkpoints - what we demonstrate to the Client at each stage. They are not payment milestones from the team’s perspective; do not anchor estimates to anything other than effort.

| # | Milestone | Trigger | Demo target |
| --- | --- | --- | --- |
| M1 | Kickoff complete | Repo set up, environments provisioned, team onboarded, Day 1 checklist done | Internal - tech lead reviews repo + env |
| M2 | Device connection verified | One eSSL device in Surendranagar HQ pushing live punches into MAMS dev environment | Demo to Client at Surendranagar; written acceptance required from Client |
| M3 | Build complete & internal QA passed | All Phase 1 modules built; Smart Anchor v2 unit tests passing; full internal QA cycle complete; bug list documented | Demo to Client; written acceptance required |
| M4 | UAT passed & errors fixed | UAT cycle at Surendranagar complete; all P1/P2 bugs closed; eSSL devices live across all 5 operational locations | Client UAT sign-off in writing |
| M5 | Final handover | Deployment on Client server complete; training delivered; full source code + DB admin creds + app admin creds + env files + deploy scripts handed over | Final written sign-off |

Important: every milestone after M1 requires explicit written acceptance from Client. There is no auto-acceptance, no deemed acceptance, no 5-day timer. If Client review is delayed beyond 10 business days, Nimit handles escalation - team continues working on next module.

## 9. Sprint plan (8 weeks of build, 2 weeks of UAT/handover)

| Week | Sprint focus | Owner |
| --- | --- | --- |
| 1 (29 Apr – 3 May) | Repo scaffold (mams-server + mams-web monorepo), CI setup, MongoDB schema design, eSSL device validation, requirements freeze | Tech lead + 1 dev |
| 2 (4 May – 10 May) | Auth module + dual-credential routing + JWT + audit-log skeleton + first eSSL push integration in dev env | Tech lead + 1 dev |
| 3 (11 May – 17 May) | Employee Master (CRUD + form validation + masking + CSV import utility) | 2 devs |
| 4 (18 May – 24 May) | Attendance Capture module + Smart Anchor v2 engine + hours decomposition + unit tests | Tech lead + 1 dev. M2 demo at end of week. |
| 5 (25 May – 31 May) | Adjustments module + approval workflow + immutable audit trail + bulk operations | 1 dev |
| 6 (1 Jun – 7 Jun) | Reports module (4 reports) + plain PDF export + CSV export + Devices module | 2 devs |
| 7 (8 Jun – 14 Jun) | Settings module + sensitive-field masking polish + visual polish + internal QA cycle 1. M3 demo at end of week. | All hands |
| 8 (15 Jun – 21 Jun) | UAT at Surendranagar HQ + bug fixes + documentation finalisation. M4 demo at end of week. | Tech lead + 1 dev on-site, others on bug-fix |
| 9 (22 Jun – 28 Jun) | Deployment to Client on-prem server + training + handover prep. M5 demo at end of week. | Tech lead on-site |
| 10 (29 Jun – 5 Jul, buffer) | Buffer week - handover polish, knowledge transfer, AMC handoff if applicable | All hands available for warranty support |

## 10. Definition of Done - applies to every task

A task is not “done” until all of the following are true:

- Code merged to main via pull request with at least one approval.

- All new code has TypeScript strict-mode types (no any without // eslint-disable-next-line and a comment explaining why).

- Unit tests for any new logic; test coverage on the changed file does not regress.

- Linter passes; Prettier formatted; no console.log left in production code.

- If the task touches an API: request + response shape documented in shared/types.

- If the task touches a sensitive-field path or audit trail: explicit audit-log entry verified by a test.

- If the task touches the on-prem deployment: deployment runbook updated.

- If the task changes user-visible behaviour: User Manual updated (or ticket created if doc lag is intentional).

## 11. Repository, branching, CI

mams/
├── mams-server/          # Express + Mongoose + TS
├── mams-web/             # Vite + React + TS + Tailwind
├── shared/types/         # Zod schemas + inferred TS types - single source of truth
├── ops/
│   ├── nginx.conf
│   ├── pm2.ecosystem.json
│   └── deploy.sh
├── docs/                 # User Manual, Admin Guide, SAD (markdown source)
└── .github/workflows/
    └── ci.yml            # lint + typecheck + test on every PR

- Branching: main is always deployable. Feature branches off main, named feat/<module>-<short-desc>. Bugfix branches fix/<short-desc>. PRs require one reviewer + green CI.

- Commit messages: Conventional Commits (feat:, fix:, docs:, refactor:, test:).

- No force-push to main. No skipping CI.

- Pre-commit hook: runs lint + typecheck + smoke unit tests locally.

## 12. Compliance & audit obligations

These are not optional. Build them in from day one.

- DPDP Act 2023 alignment: lawful basis (employer-employee), data-minimisation (masking), purpose limitation (no use of Client data for any non-Makson purpose ever - no demos, no training datasets, nothing), 72-hour breach notification path documented, data subject rights (access, correction, erasure-on-leave) exposed via API.

- SPDI Rules 2011: TLS 1.2+ in transit; encryption at rest at the volume level (Client’s responsibility on on-prem server) and at the field level for the five sensitive fields.

- No personal data leaves the Client server. No analytics SDKs, no error reporting (Sentry, Bugsnag, etc.), no cloud logging. Logs go to local files, rotated by logrotate.

- Audit log completeness is reviewed in the M3 internal QA cycle as a release blocker.

- Engagement is strictly limited to Makson Pharmaceuticals (India) Pvt. Ltd. as a single legal entity. No data from any group/sister/affiliate company. If Client asks about extending coverage to another entity, escalate to Nimit - separate engagement required.

## 13. Risks & mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| eSSL device on a model we haven’t tested fails compatibility | Medium | High | Validate every nominated model in Week 1–2. Maintain compatibility matrix. Escalate to Nimit if a model fails. |
| Client server provisioning delayed | Medium | High | Local Docker dev environment in Week 1; can demo from dev box if Client server slips. Push Client weekly via Nimit. |
| Smart Anchor edge case (DST? leap second?) | Low | Medium | India does not observe DST. Use Asia/Kolkata throughout. Test midnight rollover and year-boundary cases explicitly. |
| Audit log volume blows up disk | Low | Medium | Log rotation: monthly partitions; archive old logs to cold storage on Client server. |
| Dev team accidentally adds a Phase 2 feature | Medium | Medium | This SoW + tech lead PR review. If anyone is unsure, ask. |
| Sensitive-field masking forgotten on a new view | Medium | High | Centralise masking in a <MaskedField> component. Lint rule: any field name matching aadhaar¦pan¦bankAccount¦pfNumber¦esiNumber rendered without <MaskedField> fails CI. |
| MongoDB on-prem performance issue | Low | Medium | Index review at end of Sprint 4. Load test with 10K rows + 50 concurrent users in Sprint 6. |
| UAT throws up a major change request | Medium | High | Strict change control - any Client request not in this SoW goes through Nimit, who decides Phase 1 vs Change Request vs Phase 2. |

## 14. Team roles

| Role | Responsibility |
| --- | --- |
| Tech Lead (Prem Mehta) | Architecture decisions, PR review, Smart Anchor v2 ownership, on-site demos at Surendranagar (M2, M4, M5), handover prep |
| Senior Full-stack Dev (×1) | Auth, Employee Master, Adjustments - the backend-heavy modules |
| Mid Full-stack Dev (×1) | Reports, Devices, Settings - the frontend-heavy modules |
| Junior Full-stack Dev (×1) | CSV import, audit log UI, helper utilities - pair with senior |
| QA / Tester | UAT cycles, regression testing, sensitive-field masking verification, bug triage |
| DevOps (part-time) | On-prem server bootstrap, Nginx config, PM2 setup, deployment runbook |
| Project Lead (Nimit) | Client SPOC, requirements clarification, milestone sign-off coordination, escalation point |

## 15. Communication

- Daily standup: 15 min, 9:30 AM IST, async-friendly (Teams thread acceptable for distributed days).

- Sprint review: end of each week (Friday 5 PM), 30 min, demo + retro.

- Tech-lead 1:1 with Nimit: Mon + Thu, 30 min, status + risks.

- Client comms: Nimit only. No team member emails Client directly. If Client emails a team member, forward to Nimit immediately.

- Microsoft Teams channels: #mams-dev, #mams-bugs, #mams-deploy.

- Asana for sprint backlog and tickets.

## 16. What “good” looks like at handover (M5)

- Client can log in as both hr.admin and hr.compliance and see their respective views.

- Real eSSL devices at all 5 active factory locations are pushing punches into MAMS in real time.

- HR can run any of the 4 reports for any date range and export to PDF/CSV.

- HR can correct attendance via the Adjustments module with full audit trail.

- All sensitive fields are masked; only hr.admin can unmask, with audit log entries for every unmask.

- The Client’s IT admin has been trained on the Admin Setup Guide and can restart, redeploy, and restore from backup.

- All source code, credentials, and runbooks have been transferred. The Client controls the system end-to-end.

- We are home before week 11 with a clean handover.

Questions on this scope go to Nimit. Do not raise them with the Client directly.