DEVELOPER HANDOFF

MAMS - Makson Attendance Management System

| Project | Makson Attendance Management System (MAMS) |
| --- | --- |
| Client | Makson Pharmaceuticals (India) Pvt. Ltd. |
| Provider | Infoloop Technologies LLP |
| Project Lead / SPOC | Mr. Nimit Kaneria - Nimit.Kaneria@infoloop.co - +91 97261 81000 |
| Kickoff | Wednesday 29 April 2026 |
| Target Handover | Week of 24 June 2026 (8-10 weeks) |
| Document Version | v1 - 30 April 2026 |

APPROVED MOCKUP REFERENCE The interactive UX prototype lives at https://makson-payroll-mockup.netlify.app — this is the visual and behavioural source of truth for Phase 1 build. Implementation should match the mockup unless this document explicitly says otherwise. Any deviation must be approved by the project lead.

## 1. WHAT YOU HAVE RECEIVED

This handoff package contains everything the engineering team needs to build MAMS Phase 1, organised in a single mams-handoff/ folder:

| Category | Where | What |
| --- | --- | --- |
| Master context | CLAUDE.md | Project context, house rules, decisions already made. Read first. |
| Transmittal | DEVELOPER-HANDOFF.md | This document - reading order, quick start, sprint plan |
| Functional scope | docs/development-scope.md (+ DOCX/PDF) | What the team is being asked to build, module by module |
| Technical specs | docs/tech/ | 4 branded PDFs: SAD, DB Schema, eSSL ADMS, Setup Guide |
| Production scaffold | mams/ | MERN monorepo, runnable. The starting codebase. |
| Visual reference | mockup/ and mockup-vite/ | The approved UX prototype, in two flavours |
| Approved mockup live | https://makson-payroll-mockup.netlify.app | The deployed mockup the Client signed off on |
| Legal docs (reference) | final-docs/v2/ | Signed contractual scope. Team does not sign these but should know what was committed. |
| Dev server config | .claude/launch.json | Pre-configured dev server launchers |

## 2. READING ORDER (FIRST 4 HOURS)

Read these in this order. Do not skip ahead.

| # | Time | Document | Why |
| --- | --- | --- | --- |
| 1 | 15 min | CLAUDE.md | Project context. The single most important document. |
| 2 | 10 min | DEVELOPER-HANDOFF.md (this doc) | Reading order + sprint plan |
| 3 | 30 min | docs/development-scope.md | All 8 modules in functional detail, IN and OUT scope |
| 4 | 60 min | docs/tech/01_System_Architecture_Document.pdf | Tier breakdown, key decisions, security, deployment |
| 5 | 45 min | docs/tech/02_Database_Schema_Reference.pdf | Field-by-field collection spec - the data layer ground truth |
| 6 | 30 min | docs/tech/03_eSSL_ADMS_Protocol_Cheatsheet.pdf | Wire protocol for biometric device integration |
| 7 | 30 min | docs/tech/04_Local_Dev_Setup_Guide.pdf | Step-by-step "your laptop to running app" |
| 8 | 30 min | Browse the live mockup | Visual / behavioural source of truth |

Total: ~4 hours. After this, you should know what is being built, why it is being built that way, and how to set up your local environment.

## 3. QUICK START - FIVE COMMANDS

# 0. Make sure MongoDB is running locally brew services start mongodb-community@7.0 # or: docker run -d -p 27017:27017 mongo:7 # 1. cd into the codebase cd mams-handoff/mams # 2. Install workspace dependencies (313 packages, ~25 sec) npm install # 3. Generate JWT secrets and write .env cp mams-server/.env.example mams-server/.env sed -i '' "s¦JWT_ACCESS_SECRET=.*¦JWT_ACCESS_SECRET=$(openssl rand -base64 32)¦" mams-server/.env sed -i '' "s¦JWT_REFRESH_SECRET=.*¦JWT_REFRESH_SECRET=$(openssl rand -base64 32)¦" mams-server/.env cp mams-web/.env.example mams-web/.env # 4. Seed the database # Creates 2 users, 9 devices, 1,800 employees, ~25,000 raw punches over 7 days, # ~12,600 derived records via Smart Anchor v2. Takes ~30-60 seconds. npm run seed # 5. Run dev servers (in two terminals) npm run dev:server # http://localhost:3001 npm run dev:web # http://localhost:5173 # Login at http://localhost:5173 # hr.admin@makson-group.com / makson2026 (real, 12-hour view) # hr.compliance@makson-group.com / makson2026 (compliant, 8-hour view)

## 4. WHAT IS BUILT vs WHAT IS STUBBED

### 4.1 Built and runnable

- Monorepo + workspaces, shared Zod types.

- Auth (login, refresh rotation, lockout, audit).

- Employees - list, detail, masking, role-gated unmask, audit.

- Attendance capture - eSSL ADMS push receiver, raw insert.

- Smart Anchor v2 with 12 passing unit tests.

- Hours decomposition (real / compliant / OT / day type).

- Dashboard - stats, weekly trend.

- Audit log infrastructure with sensitive-field unmask audit.

- Web frontend (Vite + React + Tailwind) - Login, Sidebar, Dashboard, Employees list/detail, Attendance Log.

- Seed script (1,800 employees, 7 days of attendance) and eSSL device simulator.

- Nginx + PM2 ops examples.

### 4.2 Stubbed - your work to flesh out

| Module | Status | Spec reference |
| --- | --- | --- |
| Adjustments workflow | Stub returns 501 | SoW §2.4, DB Schema §7 |
| Reports (PDF / CSV export) | Stub returns 501 | SoW §2.5, SAD §5.4 |
| Devices admin (sync, registration) | Read works, mutations stubbed | SoW §2.6 |
| Settings editor (audit on change) | Read works, write stubbed | SoW §2.7, DB Schema §9 |
| CSV bulk import | TODO - not yet added | SoW §2.2 |
| E2E tests (Playwright smoke) | TODO | dev-scope §10.3 |
| Letterhead PDF + date format | PHASE 2 - DO NOT BUILD | SoW §3 |

## 5. SPRINT PLAN (8-10 WEEKS)

From the legal SoW v2 Clause 5:

| Milestone | Trigger | When | Engineering work |
| --- | --- | --- | --- |
| M1 Kickoff | Signed docs received | Week 1 | Onboarding, env validation, eSSL device compatibility check |
| M2 Device Connection Verified | eSSL pushing live in dev | End of Week 4 | Seed → CSV import → Auth hardened → eSSL receiver with real device → live attendance log |
| M3 Build Complete & QA Passed | All Phase 1 modules built | End of Week 7 | Adjustments → Reports → Devices admin → Settings editor → internal QA |
| M4 UAT Passed & Errors Fixed | Surendranagar UAT complete | End of Week 9 | UAT cycle → P1/P2 defects closed → eSSL across all 5 locations |
| M5 Final Handover & Sign-off | On-prem deploy + handover | End of Week 10 | Deploy → Manuals → training → source code + creds handover → written sign-off |

Suggested sprint cadence: 2-week sprints. Demo cadence: weekly status email + bi-weekly review call (per SoW Clause 9).

## 6. HOUSE RULES (NON-NEGOTIABLE)

From CLAUDE.md Section 12. Do not deviate without checking with the project lead.

- Never reintroduce Phase 2 features into Phase 1. Reports stay view-only with plain PDF/CSV. No letterhead PDF. No date-format standardisation. No payroll. No leave management. Aadhaar field validation is Phase 2; capture is Phase 1 (masked).

- Hours are source of truth. Never let a day-based calc sneak in. Always compute hours first, derive days last using the standard divisor of 9.5.

- Dual view at the QUERY layer, not the table layer. ONE attendance collection. The viewMode tag on the request determines which fields the API returns. No duplication of attendance records.

- Smart Anchor MUST be deterministic. Same (employeeId, date, alternateShift, realEntry, realExit) always produces the same (compliantEntry, compliantExit). Tests guard this.

- Timezone: Asia/Kolkata everywhere. Store UTC, display IST. Use date-fns-tz.

- Validate PAN + IFSC. Skip Aadhaar checksum validation in Phase 1.

- Audit log is immutable. Adjustments create new records, never mutate. The MongoDB application user has insert+find permissions only on attendance_raw, adjustments, audit_log, and unmask_audit.

- Sensitive fields masked by default, role-gated unmask, every unmask logged in unmask_audit.

- On-prem only. No cloud services at runtime. No Auth0, Sentry, S3, Mixpanel, SaaS auth, nothing. Zero outbound dependencies in production.

- Run npm run validate before every commit (typecheck + lint + tests).

## 7. OPEN QUESTIONS FOR THE PROJECT LEAD

| # | Question | Why it matters |
| --- | --- | --- |
| 1 | Confirmed list of factory locations + employee counts per location | Sizing the eSSL device count for M2 |
| 2 | Brand assets (Makson logo, favicon) - when will Client deliver? | Per SoW §12, Week 2. Block on this for branding. |
| 3 | Replacement plan for non-eSSL legacy devices (Hanvon F710) | Per SoW §12, Client cost. Need timeline from Komal. |
| 4 | Network reachability between factory locations and on-prem server | Critical for ADMS push. ~100K record offline buffer is the safety margin. |
| 5 | Static IP / DNS for the on-prem server | Devices need a stable target. |
| 6 | Approval / definition of compliance shifts | SAD assumes A=06-14, B=14-22, C=22-06 IST. Confirm with Komal. |
| 7 | UAT participants and schedule | Need 3-5 HR users at Surendranagar for M4. |

## 8. COMMUNICATION & ESCALATION

| Role | Person | Contact |
| --- | --- | --- |
| Project Lead / Infoloop SPOC | Mr. Nimit Kaneria | Nimit.Kaneria@infoloop.co · +91 97261 81000 |
| Executive Sponsor (Infoloop) | Mr. Nimit Kaneria (CEO) | as above |
| Tech Lead (Infoloop) | Mr. Prem Mehta | introduced via Project Lead |
| Client SPOC | Mrs. Komal Makasana (CFO & Partner) | introduced via Project Lead |
| Client Executive Sponsor | Mr. Kalpesh Makasana (Director) | introduced via Project Lead |

Escalation path: Engineer → Prem Mehta (Tech Lead) → Nimit Kaneria (Project Lead) → Executive Sponsor.

### 8.1 Tools

- Microsoft Teams for all team chat. Channels: #mams-dev, #mams-bugs, #mams-deploy (or whatever Prem sets up - confirm channel names on Day 1).

- Asana for sprint backlog and ticket tracking.

- Email to the Client only via Project Lead - engineers never email Komal directly without Nimit awareness.

### 8.2 Cadence

- Daily async standup in Teams #mams-dev (15 min, 9:30 AM IST, threaded).

- Weekly status email to Komal (Project Lead writes - engineers contribute one-liners).

- Bi-weekly Client review call (Project Lead + Tech Lead attend; engineers may be invited for technical demos).

- Engineers should never email or message the Client directly without Project Lead awareness.

## 9. PRE-KICKOFF CHECKLIST

Things to do before writing your first line of MAMS code on Wednesday 29 April:

- Read all four documents in §2 reading order.

- Working local environment (per Quick Start §3); seeded DB; both dev servers up; can log in as both hr.admin and hr.compliance.

- Initialise the Git repo from this ZIP - the team owns the initial commit. Run git init, add a .gitignore-respecting initial commit, push to the Infoloop Git host, configure branch protection on main. The ZIP is delivered without .git history.

- Confirmed access to Microsoft Teams channels (#mams-dev, #mams-bugs, #mams-deploy - Prem will confirm names).

- Confirmed access to the Asana project / workspace.

- You can run npm run validate and it passes.

- You have read the approved mockup and clicked through every screen.

- You have skim-read legal SoW v2 Clauses 2, 3, 5, 6, 7, 8, 11.

## 10. DAY 1 TASK IDEAS

Small things to ship on Day 1 to learn the codebase. Pick one, open a PR, get it merged, then start real work:

- Add a CSV employee-import endpoint stub (POST /api/employees/import-csv) returning 501. Wire up an "Import CSV" button on Employees page.

- Add a /health ping in the web header that calls GET /api/health every 30s and shows a green/red dot.

- Write one Vitest unit test for the masking helper at mams/mams-server/src/utils/mask.ts.

- Read the Sidebar component and add a small "Build version" footer using import.meta.env.VITE_APP_VERSION.

CLOSING NOTE The scaffold is intentionally not 100% complete. It is a foundation that proves end-to-end correctness for the hardest parts (auth, dual-credential view, eSSL receiver, Smart Anchor v2, sensitive-field masking) and leaves the workflow-heavy modules (Adjustments, Reports, Devices admin, Settings) for the team. Read carefully. Run the scaffold. Click through the mockup. Then write code. Welcome aboard.